Project Management System Customization(BRD)

June 12, 2026

Document Version:   1.0 | Initial

# Document Information

| Item | Description |
| --- | --- |
| Project Name | Project Management System Customization |
| System | Odoo ERP |
| Business Owner | Ahadu Bank |
| Prepared By | Enterprise Program and Architecture Division |
| Abroved by | IT Program management &Innovation department |
| Document Type | Business Requirement Document (BRD) |
| Version | 1.0 |
| Date | June 2026 |

Table of Contents

Document Information	i

1.	Introduction	3

2.	Business Objectives	3

3.	Scope	3

3.1	In Scope	3

3.2	Out of Scope	4

4.	Stakeholders	4

5.	Functional Requirements	5

5.1	Project Registration and Management	5

5.2	Project Work Breakdown Structure (WBS)	6

5.3	Task Management	8

5.4	Project Scheduling	9

5.5	Resource Management	10

5.6	Timesheet Management	11

5.7	Project Budget Management	11

5.8	Risk Management	12

5.9	Issue Management	12

5.10	Change Request Management	13

5.11	Milestone Management	14

5.12	Project Document Management	14

5.13	Project Approval Workflow	15

5.14	Dashboard and Reporting	16

5.15	Notifications and Alerts	16

5.16	Integration Requirements	17

6.	Security Requirements	17

7.	Project Closure Management	18

8.	Non-Functional Requirements	19

9.	Expected Benefits	19

# Introduction

Ahadu Bank is implementing Odoo ERP to streamline and automate its internal business processes. To improve project governance, planning, execution, monitoring, and reporting across the Bank, the Project Management Module requires customization to align with Ahadu Bank’s project management framework, approval workflows, governance requirements, and reporting standards.

The customized solution will provide centralized management of all strategic, operational, technology, infrastructure, compliance, and business projects undertaken by the Bank.

# Business Objectives

The objectives of the Project Management System are to:

- Centralize IT project management activities across the Bank.

- Improve project planning and execution.

- Enhance visibility into project status and performance.

- Facilitate effective resource allocation and utilization.

- Strengthen project governance and approval processes.

- Improve project budget control and monitoring.

- Enable real-time reporting and decision-making.

- Maintain complete audit trails for all project activities.

- Support project portfolio management initiatives.

# Scope

## In Scope

The customization shall include:

- Project Registration

- Project Planning

- Task Management

- Resource Management

- Timesheet Management

- Budget Management

- Risk Management

- Issue Management

- Change Request Management

- Milestone Tracking

- Document Management

- Approval Workflow

- Dashboards and Reports

- Notifications and Alerts

- Integration with HR and Finance Modules

- Project Closure Management

## Out of Scope

- Procurement Management

- Vendor Contract Management

- Asset Management

- External Customer Project Management

# Stakeholders

| Stakeholder | Responsibility |
| --- | --- |
| Executive Management | Strategic Oversight |
| IT Program and innovation Office | Project Governance |
| Enterprise Program & Architecture Division | System Administration, manage Project Planning and Execution |
| Project Managers | Project Planning and Execution |
| Department directors | Resource Approval |
| Team Members | Task Execution |

# Functional Requirements

## Project Registration and Management

The Project Registration and Management module shall provide a centralized repository for creating, maintaining, and tracking all projects undertaken by Ahadu Bank. The module shall enable authorized users to register new projects, capture project-related information, assign project ownership, define project timelines, establish budgets, and monitor project status throughout the project lifecycle.

The module shall serve as the foundation for all project management activities by ensuring that every project is formally recorded, approved, and governed according to the Bank's project management framework.

- Functional Requirements

The system shall allow authorized users to:

- Create new project records.

- Update project information.

- Assign project sponsors and project managers.

- Define project start and end dates.

- Categorize projects based on project type.

- Monitor project progress and status.

- Archive completed projects.

- Search and retrieve project information.

- Required Information

The system shall capture the following information for each project:

| Field | Description |
| --- | --- |
| Project ID | System-generated unique identifier for each project. |
| Project Name | Official name of the project. |
| Project Code | Unique project reference code used for reporting and tracking. |
| Project Category | Classification of the project, such as Strategic, IT Application, IT Infrastructure, IT Security, Business Improvement, Compliance, or Regulatory. |
| Project Sponsor | Higher management official accountable for project success and funding. |
| Project Manager | Individual responsible for planning, execution, monitoring, and closure of the project. |
| Department | Business unit responsible for initiating or owning the project. |
| Start Date | Planned commencement date of the project. |
| End Date | Planned completion date of the project. |
| Budget | Approved budget allocated for project execution. |
| Priority | Project importance level (High, Medium, Low). |
| Status | Current lifecycle status of the project. |
| Description | Detailed description of the project objectives, scope, and expected outcomes. |

- Workflow

Draft → Submitted → Approved → Active → Closed

- Business Rules

- Every project shall have a unique Project ID.

- A project cannot become Active unless approved.

- Every project shall have an assigned Project Sponsor and Project Manager.

- Project start and end dates shall be mandatory.

- Only authorized users may modify approved projects.

- Any significant modification to an approved project shall require approval.

## Project Work Breakdown Structure (WBS)

The Work Breakdown Structure (WBS) module shall enable project managers to decompose projects into manageable components and activities. The WBS shall provide a hierarchical structure that improves planning, monitoring, accountability, and progress tracking throughout the project lifecycle.

The module shall support the organization of projects into programs, phases, milestones, tasks, and sub-tasks, enabling stakeholders to understand project scope and responsibilities clearly.

- Functional Requirements

The system shall:

- Create hierarchical project structures.

- Define project phases and milestones.

- Create tasks and sub-tasks.

- Assign responsibility for each activity.

- Establish task dependencies.

- Track completion progress at each level.

- Roll up progress from task level to project level automatically.

- Components

| Component | Description |
| --- | --- |
| Project | The highest-level initiative being managed. |
| Program | A group of related projects managed together. |
| Phase | Major stages of project execution. |
| Milestone | Significant achievement or deliverable within a project. |
| Task | Individual activity required to complete a project phase. |
| Sub-task | Smaller activity under a task. |

- Business Rules

- Projects may contain multiple phases.

- Each phase may contain multiple milestones.

- Each milestone may contain multiple tasks.

- Tasks may contain sub-tasks.

- Dependencies between tasks shall be supported.

- Project progress shall be calculated based on task completion percentages.

## Task Management

The Task Management module shall enable project managers to plan, assign, monitor, and control project activities. The module shall provide visibility into task ownership, progress, deadlines, and workload, ensuring accountability and timely project execution.

The system shall support task creation, assignment, prioritization, status tracking, collaboration, and performance monitoring.

- Functional Requirements

The system shall:

- Create tasks and sub-tasks.

- Assign tasks to employees or teams.

- Define task priorities.

- Monitor task progress.

- Track planned versus actual completion dates.

- Support task comments and collaboration.

- Maintain task history and audit records.

- Generate alerts for overdue tasks.

- Required Information

| Field | Description |
| --- | --- |
| Task Number | Unique identifier for each task. |
| Task Name | Name of the task. |
| Description | Detailed explanation of the activity. |
| Assigned Resource | Employee or team responsible for execution. |
| Priority | Importance level of the task. |
| Planned Start Date | Scheduled task start date. |
| Planned End Date | Scheduled task completion date. |
| Actual Start Date | Actual commencement date. |
| Actual End Date | Actual completion date. |
| Status | Current task status. |
| Completion Percentage | Percentage of work completed. |
| Attachments | Supporting files and documents. |

Status Workflow

Not Started → Assigned → In Progress → Pending → Completed → Cancelled

Additional Features

- Task comments.

- File attachments.

- Activity history.

- Dependency management.

- Automatic overdue alerts.

- Progress tracking dashboards.

Business Rules

- Every task shall be assigned to a responsible resource.

- Completion percentage shall range from 0% to 100%.

- Completed tasks cannot be modified without authorization.

- Overdue tasks shall trigger automatic notifications.

## Project Scheduling

The Project Scheduling module shall enable project managers to develop, maintain, and monitor project schedules throughout the project lifecycle. The module shall provide visibility into project timelines, task dependencies, milestone dates, and schedule performance to ensure projects are completed within approved timelines.

Functional Requirements

The system shall:

- Create project schedules.

- Define task dependencies.

- Establish project milestones.

- Display project timelines using Gantt charts.

- Monitor schedule variance.

- Identify delayed activities.

- Support critical path analysis.

- Automatically update project completion percentages.

Business Rules

- Every project shall have a baseline schedule.

- Tasks may have predecessor and successor relationships.

- Changes to approved schedules shall require authorization.

- Schedule variances shall be tracked and reported.

## Resource Management

The Resource Management module shall enable project managers to plan, allocate, monitor, and optimize project resources. The module shall provide visibility into resource availability, workload distribution, utilization levels, and capacity planning.

Functional Requirements

The system shall:

- Allocate resources to projects and tasks.

- Monitor resource utilization.

- Track resource availability.

- Identify resource conflicts.

- Manage resource workloads.

- Generate resource utilization reports.

Business Rules

- Resources shall not be assigned beyond approved capacity.

- Resource availability shall consider leave and organizational assignments.

- Resource allocation changes shall be recorded in the audit trail.

## Timesheet Management

The Timesheet Management module shall enable project team members to record actual working hours spent on project activities. The module shall facilitate effort tracking, resource productivity measurement, project costing, and management reporting.

Functional Requirements

The system shall:

- Capture employee work hours.

- Associate timesheets with projects and tasks.

- Support timesheet submission and approval.

- Track planned versus actual effort.

- Generate timesheet reports.

Business Rules

- Employees shall submit timesheets periodically.

- Timesheets shall require approval before posting.

- Approved timesheets shall not be modified without authorization.

- Hours worked shall contribute to project cost calculations.

Workflow

Draft → Submitted → Approved → Posted

## Project Budget Management

The Project Budget Management module shall enable project teams and management to plan, allocate, monitor, and control project financial resources throughout the project lifecycle.

Functional Requirements

The system shall:

- Define project budgets.

- Categorize budget components.

- Record project expenditures.

- Compare actual versus planned costs.

- Monitor budget utilization.

- Generate budget variance reports.

- Forecast project costs.

Business Rules

- Every project shall have an approved budget.

- Budget revisions shall require approval.

- Expenditures shall not exceed approved thresholds without authorization.

- Budget performance shall be reported regularly.

## Risk Management

The Risk Management module shall support the identification, assessment, monitoring, mitigation, and reporting of project risks to minimize potential impacts on project objectives.

Functional Requirements

The system shall:

- Create and maintain risk registers.

- Assess risk probability and impact.

- Calculate risk ratings.

- Assign risk owners.

- Define mitigation plans.

- Monitor risk status.

- Generate risk reports.

Business Rules

- Every risk shall have an assigned owner.

- Risks shall be periodically reviewed.

- High-risk items shall be escalated automatically.

- Closed risks shall remain available for audit purposes.

## Issue Management

The Issue Management module shall facilitate the recording, tracking, escalation, and resolution of issues affecting project execution.

Functional Requirements

The system shall:

- Log project issues.

- Assign issue owners.

- Track issue resolution.

- Escalate unresolved issues.

- Monitor issue aging.

- Generate issue reports.

Business Rules

- Every issue shall have a responsible owner.

- Critical issues shall be escalated immediately.

- Resolved issues shall require closure confirmation.

- Issue history shall be retained.

## Change Request Management

The Change Request Management module shall manage modifications to project scope, schedule, budget, deliverables, or requirements through a controlled approval process.

Functional Requirements

The system shall:

- Register change requests.

- Conduct impact assessments.

- Track approval decisions.

- Monitor implementation status.

- Maintain change history.

Business Rules

- All change requests shall undergo formal review.

- Approved changes shall update project baselines.

- Rejected changes shall remain archived.

- Impact assessments shall be mandatory before approval.

Workflow

Draft → Submitted → Reviewed → Approved → Implemented → Closed

## Milestone Management

The Milestone Management module shall enable project managers to define, monitor, and report key project achievements and deliverables throughout the project lifecycle.

Functional Requirements

The system shall:

- Create project milestones.

- Monitor milestone progress.

- Track planned and actual completion dates.

- Generate milestone reports.

- Notify stakeholders of upcoming milestones.

Business Rules

- Milestones shall be linked to project phases.

- Milestone completion shall update project progress.

- Delayed milestones shall trigger alerts.

## Project Document Management

The Project Document Management module shall provide a centralized repository for storing, organizing, controlling, and retrieving project-related documents.

Functional Requirements

The system shall:

- Upload and download documents.

- Maintain document versions.

- Restrict access based on user roles.

- Track document history.

- Archive project records.

Business Rules

- Documents shall be categorized appropriately.

- Version control shall be mandatory.

- Unauthorized users shall not access restricted documents.

- Document activities shall be audited.

## Project Approval Workflow

The Approval Workflow module shall facilitate structured review and approval processes for project initiation, budget approvals, change requests, milestone approvals, and project closure activities.

Functional Requirements

The system shall:

- Route approvals automatically.

- Support multi-level approval processes.

- Capture approval comments.

- Maintain approval history.

- Notify approvers and requestors.

Business Rules

- Approval authority shall follow organizational hierarchy.

- Approval decisions shall be recorded permanently.

- Rejected requests shall include justification.

## Dashboard and Reporting

The Dashboard and Reporting module shall provide real-time visibility into project performance, resource utilization, financial status, risks, issues, and portfolio health.

Functional Requirements

The system shall:

- Display interactive dashboards.

- Generate standard reports.

- Support report export functionality.

- Provide role-based dashboard views.

- Support ad-hoc reporting.

Business Rules

- Dashboard information shall be refreshed automatically.

- Users shall access reports based on permissions.

- Historical reporting data shall be retained.

## Notifications and Alerts

The Notifications and Alerts module shall provide automated communication regarding project activities, approvals, deadlines, milestones, and exceptions requiring attention.

Functional Requirements

The system shall:

- Send task assignment notifications.

- Notify users of upcoming deadlines.

- Alert users of overdue activities.

- Notify approvers of pending actions.

- Generate milestone reminders.

- Alert management of critical risks and issues.

Business Rules

- Notifications shall be role-based.

- Alerts shall be configurable.

- Notification history shall be retained.

## Integration Requirements

The system shall integrate seamlessly with other Odoo ERP modules and enterprise systems to ensure data consistency and eliminate duplicate data entry.

Functional Requirements

The system shall integrate with:

- Human Resource Management

- Finance and Accounting

- Document Management

- Workflow Engine

- Email Services

Business Rules

- Master employee data shall be sourced from HR.

- Financial information shall be sourced from Finance.

- Integration transactions shall be logged and auditable.

# Security Requirements

The Security Management module shall ensure confidentiality, integrity, availability, and accountability of project information through robust access controls and audit mechanisms.

Functional Requirements

The system shall:

- Implement role-based access control.

- Enforce user authentication.

- Maintain audit logs.

- Support approval history tracking.

- Protect sensitive project information.

Business Rules

- Users shall access only authorized information.

- All critical transactions shall be logged.

- System sessions shall expire after inactivity.

- Security events shall be auditable.

# Project Closure Management

The Project Closure Management module shall facilitate the formal completion of projects through validation, documentation, stakeholder sign-off, and archival activities.

Functional Requirements

The system shall:

- Execute closure checklists.

- Capture lessons learned.

- Conduct final budget reviews.

- Obtain stakeholder approvals.

- Archive project records.

Business Rules

- Projects shall not be closed with unresolved critical issues.

- Closure approval shall be mandatory.

- Archived projects shall remain accessible for reporting and audit purposes.

- Final project performance reports shall be generated automatically.

Closure Workflow

Closure Request → Review → Approval → Archive

# Non-Functional Requirements

Performance

- Support a minimum of 1,000 concurrent users.

- Dashboard response time shall not exceed 5 seconds.

Availability

- System availability shall be 99.9%.

Scalability

- Support future expansion of projects and users.

Auditability

- Maintain complete audit records of all project transactions.

Usability

- Responsive web-based interface.

- Mobile-friendly access.

Compliance

- Maintain project records for a minimum of seven (7) years.

# Expected Benefits

The customized Project Management Module will enable Ahadu Bank to:

- Improve project governance and transparency.

- Increase project delivery success rates.

- Enhance resource utilization.

- Improve budget monitoring and control.

- Strengthen executive visibility through real-time dashboards.

- Standardize project management practices across the Bank.

- Maintain compliance with internal governance and audit requirements.